## Gantt Chart - Manual End Date
[7 empty] | Team or Instructor: | Hardware Team | Slam S Team | Slam Ma Team | Slam Mb Team | Context Awareness A Team | Context Awareness B Team | Motion Control Planning Team
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete
Maximum Height Definition | 2017-01-27 | 2017-02-03 | 7 | 3.5 | 3.5 | 50% |  | R | R | R | R
Interface Hardware/Sotware on Tx1 - Stereo | 2017-01-27 | 2017-02-03 | 7.25 | 1.75 | 5.25 | 25% |  |  | R | S | S
Define Hardware and Software used | 2017-01-27 | 2017-02-03 | 7 | 5.6 | 1.4 | 80% |  | R | R | R | R | R | R | R
Control Interface Implementation (using ROS) in Simulation | 2017-02-03 | 2017-02-10 | 7 | 0 | 7 | 0% |  | S | [5 empty] | R
Motor Control Functionality with ROS | 2017-01-27 | 2017-02-10 | 14 | 2.8 | 11.2 | 20% |  | R
Define Interfaces used | 2017-01-27 | 2017-02-10 | 14 | 4.9 | 9.1 | 35% |  | R | R | R | R | R | R | R
Implement SLAM on TX1 - Monocular A | 2017-02-03 | 2017-02-10 | 7 | 0 | 7 | 0% |  |  | R | S | S
ZED Calibration | 2017-02-03 | 2017-02-10 | 7 | 0 | 7 | 0% |  |  | R
ROS Definition | 2017-01-27 | 2017-02-10 | 14 | 12.6 | 1.4 | 90% |  | R | R | R | R | R | R | R
Localization Scheme Implementation for Husky | 2017-02-03 | 2017-02-17 | 14 | 0 | 14 | 0% | [7 empty] | R
Simulated Environment | 2017-02-03 | 2017-02-17 | 14 | 0 | 14 | 0% | [5 empty] | S | R | S
Finalize SLAM Interface with ctx Awareness - Monocular A | 2017-02-10 | 2017-02-17 | 7 | 0 | 7 | 0% |  |  | R | S | S | S | S
Update Husky model with Cameras and LIDAR | 2017-02-10 | 2017-02-20 | 10 | 0 | 10 | 0% |  | S | S | S | S |  |  | R
Deploy Rtab and Orb SLAM | 2017-02-10 | 2017-02-24 | 14 | 0 | 14 | 0% |  |  | R | S | S
Power Supply Integration | 2017-01-27 | 2017-02-24 | 28 | 5.6 | 22.4 | 20% |  | R
Camera Data Interface | 2017-02-10 | 2017-02-24 | 14 | 7 | 7 | 50% |  | R | R | R | R
Frame Apparatus Completion | 2017-02-03 | 2017-02-24 | 21 | 5.25 | 15.75 | 25% |  | R
SLAM Stereo Team Indoor Test | 2017-02-20 | 2017-03-03 | 11 | 0 | 11 | 0% |  |  | R
Survey Packages for Sensor Simulation | 2017-02-20 | 2017-03-03 | 11 | 0 | 11 | 0% |  | S | [5 empty] | R
Establish Control of Husky in Psyical World | 2017-02-20 | 2017-03-03 | 11 | 0 | 11 | 0% |  | S | [5 empty] | R
Indoor testing - Monocular A | 2017-02-17 | 2017-03-03 | 14 | 0 | 14 | 0% |  |  | R | S | S
PTU Integration | 2017-01-27 | 2017-03-03 | 35 | 0 | 35 | 0% |  | R | R | S | S
Indoor Enviornment | 2017-02-17 | 2017-03-10 | 21 | 0 | 21 | 0% | [5 empty] | S | R | S
Live Demo Data Transmission | 2017-03-03 | 2017-03-17 | 14 | 0 | 14 | 0% |  | R | R | R | R | R | R | R
CUDA Optimizations SLAM Stereo | 2017-03-03 | 2017-03-28 | 25 | 0 | 25 | 0% |  |  | R | S | S
Test SLAM Stereo Outdoors | 2017-03-03 | 2017-03-28 | 25 | 0 | 25 | 0% |  |  | R
Implement Navigation Algorithm | 2017-03-03 | 2017-03-28 | 25 | 0 | 25 | 0% | [5 empty] | S | S | R
Outdoor Testing - Monocular A | 2017-03-03 | 2017-03-31 | 28 | 0 | 28 | 0% |  |  | R | S | S
Outdoor Enviornment | 2017-03-10 | 2017-03-31 | 21 | 0 | 21 | 0% | [5 empty] | S | R | S
Algorithm Integration | 2017-02-10 | 2017-03-31 | 49 | 0 | 49 | 0% |  | R | R | R | R | R | R | R
Indoor testing | 2017-03-31 | 2017-04-07 | 7 | 0 | 7 | 0% |  | R | R | R | R | R | R | R
Software Integration with all components | 2017-03-28 | 2017-04-14 | 17 | 0 | 17 | 0% |  | S | S | S | S | S | S | R
Integration with ROS | 2017-03-31 | 2017-04-14 | 14 | 0 | 14 | 0% |  | S |  |  |  | S | R | S
Outdoor Testing | 2017-04-07 | 2017-04-23 | 16 | 0 | 16 | 0% |  | R | R | R | R | R | R | R
Field Test for all systems | 2017-04-23 | 2017-04-30 | 7 | 0 | 7 | 0% |  | R | R | R | R | R | R | R
R - Requried
S - Support